## CS
Confidence Infrastructure Limited
Project: 5000 TPD VRM Mill of Confience Cement Dhaka Limited.
Location: Danga Bazar, Polash, Narsingdhi, Dhaka
High Level Comparative Statement for RM Shed Pilling Foundation Cost
OPTION-1 Shed Size:170x45m and 5m Holding Wall with total Capacity of 32,000 MT
SL No | Description of Work | Unit | Quantity | Quantity | Rate | Amount (BDT-TK) | Remarks
1 | 542 nos Pile Boring /Drilling ( 800mm dia) 40M Long | RM |  | 21680 | 2100 | 45528000
2 | 542 nos Pile M.S Rebar | M.T |  | 800 | 90000 | 72000000
3 | 542 nos Pile Concrete | CUM |  | 10897.5566 | 11000 | 119873122.5645
Total Amount (TK) = | [5 empty] | 237401122.5645
OPTION-2 Shed Size:170x45m and 1.5m Holding Wall with total Capacity of 32,000 MT (CHMC will Confirm the Capacity)
SL No | Description of Work | Unit | Quantity | Quantity | Rate | Amount (BDT-TK) | Remarks
1 | 89 nos Pile Boring /Drilling ( 1000mm dia) 40m Long | RM |  | 3560 | 2600 | 9256000
2 | 89 nos Pile M.S Rebar | M.T |  | 205.2583 | 90000 | 18473247.2325
3 | 89 nos Pile Concrete | CUM |  | 2796.0175 | 11000 | 30756192.0786
Total Amount (TK) = | [5 empty] | 58485439.3111
Difference between Option-1 and Option-2 (TK) = | [5 empty] | 178915683.2534

## Details
High Level Comparative Statement for RM Shed Foundation
OPTION-1
SL No | Description of Work | Unit | Per Pile | Number | Quantity | Rate | Remarks
1 | 542 nos Pile Boring /Drilling | RM | 40.7 | 542 | 22059.4 | 2100
2 | 542 nos Pile M.S Rebar | M.T | 1.48 | 542 | 800 | 90000
3 | 542 nos Pile Concrete | CUM | 0.5 | 542 | 10900 | 11000
4 | Remaining Concrete Quantity (Area of RM Shed 170m x 45m) considering 600mm thick slab | Cum | 170m x 45m x 600mm |  | 4600 | 14000
OPTION-2
SL No | Description of Work | Unit | Per Pile | Number | Quantity | Rate | Remarks
1 | 89 nos Pile Boring /Drilling | RM | 40.7 | 89 | 3622.3 | 2600
2 | 89 nos Pile M.S Rebar | M.T | 3.48 | 89 | 310 | 90000
3 | 89 nos Pile Concrete | CUM | 32 | 89 | 2800 | 11000
4 | Remaining Concrete Quantity (Area of RM Shed 190m x 60m) | Cum | 170m x 45m x 600mm |  | 4600 | 14000

## Storage
Slag Shed Capacity Calculation
Holding Wall Height | Area of Transverse Section, A | Straight Length, Ls | Tapered Length, Lt | Volume of Straight Length, Vs = A x Ls | Volume of Straight Length, Vt = 1/2 A x Lt | Total Volume, V= Vs + Vt | Slag Capacity, Ts=1.05xV | All are theoretical Calculation. Practical Calculation from CHMC:- Slag: 20,000 MT, Limestone: 6000 MT, Gypsum: 6000 MT with 5m Holding wall
m | Sqm | m | m | Cum | Cum | Cum | MT
5 | 272 | 77.28 | 29.72 | 21020.16 | 4041.92 | 25062.08 | 26315.184
2.5 | 238 | 77.28 | 29.72 | 18392.64 | 3536.68 | 21929.32 | 23025.786
1.5 | 194.5 | 77.28 | 29.72 | 15030.96 | 2890.27 | 17921.23 | 18817.2915
Limestone/Gypsum Shed Capacity Calculation (Considering Circular Base)
Holding Wall Height | Radius of the Base, r | Area of the Base, Pi*r^2 | Height of the Holding Wall, Hw | Height of the Cone, Hc | Volume of Holding Wall, Vw = A x Hw | Volume of Cone, Vc = 1/3 A x Hc | Total Volume, V = Vw + Vc | Limestone/Gypsum Capacity, Ts=1.35xV
m | m | Sqm | m | m | Cum | Cum | Cum | MT
5 | 15 | 706.8583 | 5 | 10 | 3534.2917 | 2356.1945 | 5890.4862 | 7952.1564
2.5 | 15 | 706.8583 | 2.5 | 10 | 1767.1459 | 2356.1945 | 4123.3404 | 5566.5095
1.5 | 15 | 706.8583 | 1.5 | 10 | 1060.2875 | 2356.1945 | 3416.482 | 4612.2507
Mill Capacity - TPD | 6000 |  |  |  | 6000
Ingredients | Ratio |  | Storage Capacity |  |  | Days to Feed
Clinker | 50% | 50% | 60000 | 60000 | 60000 | 20 | 20 | 20
Fly Ash | 21% | 21% | 10000 | 10000 | 10000 | 7.9365 | 7.9365 | 7.9365
Slag | 21% | 21% | 20000.1398 | 17500.1224 | 14301.5706 | 15.8731 | 13.889 | 11.3505
Limestone | 5% | 5% | 6000.118 | 4200.0826 | 3480.0684 | 20.0004 | 14.0003 | 11.6002
Gypsum | 3% | 3% | 6000.118 | 4200.0826 | 3480.0684 | 33.334 | 23.3338 | 19.3337
0.76002 | 100% | 100% | 102000.3759 | 95900.2876 | 91261.7075
0.75453